## Cover
An illustration of the application of Failure Modes and Effects Analysis (FMEA) techniques to the analysis of information security risks
Introduction and acknowledgement
The original version of this spreadsheet was kindly provided to the ISO27k Implementers' Forum by Bala Ramanan to demonstrate how the FMEA method can be used to analyze information security risks. Subsequently, Bala kindly agreed to donate it to the ISO27k Toolkit. Apart from minor updates and reformatting, it is essentially unchanged. We are very grateful for Bala's input.
Contents
The FMEA Sample tab has the actual illustration - an analysis of possible failure modes for a firewall.
The Guidelines provide additional notes on the FMEA method, including a step-by-step process outline.
The Severity, Probability and Detectability tabs have tables demonstrating scales commonly used to rank risks by these criteria.
Copyright
This work is copyright © 2008, ISO27k Forum, some rights reserved. It is licensed under the Creative Commons Attribution-Noncommercial-Share Alike 3.0 License. You are welcome to reproduce, circulate, use and create derivative works from this provided that (a) it is not sold or incorporated into a commercial product, (b) it is properly attributed to the ISO27k Implementers’ Forum at www.ISO27001security.com, and (c) derivative works are shared under the same terms as this.
Disclaimer
Risk analysis is more art than science. Don't be fooled by the numbers and formulae: the results are heavily influenced by the accuracy of the users' assessment of risk factors, by the definition of information assets and by the framing of risks being considered. For these reasons, the process is best conducted by a team of people with solid expertise and practical experience of (a) assessing and managing information security risks, and (b) the organization, its internal and external situation with respect to information security. Don't expect to get definitive answers from anyone. It is impossible to guarantee that all risks have been considered and analyzed correctly. Some very experienced practitioners in this field claim that all risk analysis is basically bunkum, and we have some sympathy with that viewpoint.
The results of the analysis should certainly be reviewed by management (ideally including IT auditors, Legal, HR, other support functions and/or information security consultants) and may be adjusted according to their experience, so long as the expert views are taken into consideration. Remember: just because the organization has little if any experience of a particular informaiton security risk does not necessarily mean that it can be discounted. Organizations with immature security management processes and systems may have significant ongoing security incidents that are not even recognized, due to inadequate incident detection and reporting processes.

## Guidelines
Guideline to Carry out a Risk Assessment Using FMEA
Important notes:
This method does not consider asset values. Rrisks are identified for each asset and prioritized without taking account of the asset values.
The Cumulative risk for the identified asset for each threat is ascertained by the Risk Priority Number (RPN)
Each asset can have more than one failure mode and for each failure mode there can be more than one vulnerability
How to carry out the Risk Assessment (RA) using FMEA:
1 | Identify the assets or the services rendered by the department under the scope of RA
5 | Now identify the failure modes for the identified asset/function. Please note that there could be more than one vulnerabilities for each asset
6 | Now identify the impact if the identified failure mode happens. That if the identified failure mode happens what will be the effect on the business or service.
7 | Now refer the impact chart and choose the number relevant to the effect of the failure mode
8 | Now identfiy the cause for the failure mode. Please note that each vulnerability can be linked with more than one threat.
9 | Now refer to the probability chart and choose the number that is more relevant to the frequency of the threat happening.
10 | Now list down the current controls. Kindly categorize the controls as preventive and detective controls. Write each control in separate rows.
11 | Now refer to the vulnerability chart and choose a number relevant to the size of vulnerability for each asset and the effectiveness of the controls that might have.
12 | Input all three in the corresponding fields. You can now see the Risk Priority Number calculated for a failure mode of the respective asset function.
13 | Now if the RPN is not under the acceptable value then the risk status shows "HIGH RISK", recommendation to mitigate each of these HIGH RISK has to be listed down. Kinldy list each control in separate rows.
Using prioritized risks
Management may decide to target, say, the top 5% of risks initially. This is an arbitrary value that can be reviewed/adjusted later.
Following the FMEA method, the risks are assessed, RPNs calculated and then risks are ranked by RPN.
5% of 1000 (the maximum RPN value) is 50. So any RPN above 50 requires review and (probably) control improvements.
All risks with RPNs above 50 are identified as "HIGH RISK". This criterion is of course based on the arbitrary 5% value noted above.
If the organization is well controlled with relatively few HIGH RISK items, the 5% value may be extended to, say 15% to address lower risks.
Alternatively, if there are simply too many HIGH RISK items to tackle at once, they may be addressed in top-down sequence according to the RPNs.
The prioritized list of risks provides management with a rational basis for determining how much resource to apply to risk reduction: the cutoff point should go further down the list if more resources are allocated, and vice versa.

## FMEA Sample
Asset Name | Function | Potential Vulnerability | Potential Threat | Potential Business Consequence (Impact) | Impact | Likelihood | Current Controls |  | Vulnerability | RPN
[7 empty] | Preventive Controls | Detective Controls
Database server | To block unauthorized requests | SQL Injection | Illegitimate access | Leakage of personal data | 10 | 4 |  |  | 3 | 120
Main Router Cisco 2911 | Network | No support / IT service not available / No backup device | Technical failure | Inability to process electronic transactions | 8 | 3 | Procedures available |  | 3 | 72
Main Router Cisco 2911 | Network | Default username / password | Interception of communications | Confidentiality breach on Financial data (cards) | 9 | 3 | Procedures available |  | 3 | 81
Hotel Guest Data | Personal information | Database not encrypted | Malicious users steal private guest data | Disclosure or modification of personal information | 9 | 8 |  | Log Monitoring | 8 | 576
Web server | Input employee data | XSS attack | Illegitimate access | Inability to process electronic transactions | 8 | 3 | Procedures available |  | 3 | 72
Workstation | Payment Process Reservation Process Order Process | remote code execution | Illegitimate access | Inability to process electronic transactions | 8 | 2 |  |  | 8 | 128
MacBook Pro 13.3 | business administration use | memory coraption CVE-2015-7104 | file modification but not full access in the machine | modification of sensitive business administration data | 5 | 2 | firewall available |  | 6 | 60
Broadband access server | internet destribution | Execute CodeOverflow CVE-2018-8136 | Broadband Server Down | no internet | 8 | 2 | firewall available |  | 6 | 96
File server | stores sensitive and non sensitive files of the hotel | Execute CodeOverflow CVE-2018-8136 | Illegitimate access to all files | Leakage of sensitive buisnes data | 8 | 2 | firewall available |  | 6 | 96
Fortinet (firewall) | filtering ingoing trafic | (Cross-site scripting (XSS) CVE-2010-0475) | Technical failure | Inability to use the information system | 9 | 1 |  |  | 2 | 18
Routers | conects devices to the network | defualt passwords no updates | Interception of communications | Confidentiality breach on Financial data (cards) | 8 | 4 | Procedures available |  | 3 | 96
Paper documents | stored data | easy access | document forging | Integrity breach on Financial data | 7 | 4 |  |  | 7 | 196
Servers | Network infurstracture | Not Server Roome available | Operations error | Inability to process electronic transactions | 8 | 5 |  |  | 7 | 280
Servers | Network infurstracture | Not secondary a/c unit | Technical failure | Inability to use the information system | 8 | 6 | primary a/c available |  | 4 | 192
Servers | Network infurstracture | Easy personnel access | Malisius employe intent | Inability to use the information system | 8 | 1 |  |  | 7 | 56
Workstation | Payment Process Reservation Process Order Process | No antivirus installed | Introduction of damaging or disruptive s/w | Inability to use the information system | 8 | 6 |  |  | 8 | 384
Personel | hotel function | No security traning no security culture | Inpersonation | Leakage of personal data | 7 | 7 |  |  | 7 | 343
Router | Network | No secundary router | Technical failure | Inability to process electronic transactions | 8 | 2 | primary router available |  | 4 | 64
Process | Programms | No software maintanance contract | Application software failure | Inability to process electronic transactions | 8 | 6 |  |  | 8 | 384
Note on B2: List down the fucntion or purpose of the asset. If more than one purpose is identified for the identified service list them down separately
Note on C2: In what all ways the service running on this asset can fail? ie the vulnerabilities List down each failure mode separately
Note on D2: if the vulnerability happens, then what could be the effect of the failure? If there is more than one failure list them seperately
Note on F2: Refer Severity Table
Note on G2: Refer Probabilty Table
Note on H2: Identify the current controls vis a vis preventive and detective controls. If there are more than one, then list them separately
Note on J2: Refer Detection table

## Impact
Effect | Impact of Threat realisation | Ranking
Catastrophic | Resource not available / Problem unknown | 10
Extreme | Resource not available / Problem known and cannot be controlled | 9
Very High | Resource not available / Problem known and can be controlled | 8
High | Resource Available / Major violation of policies | 7
Moderate | Resource Available / Major violations of process | 6
Low | Resource Available / Major violations of procedures | 5
Very Low | Resource Available / Minor violations of policies | 4
Minor | Resource Available / Minor violations of process | 3
Very Minor | Resource Available / Minor violations of procedures | 2
None | No effect | 1

## Likelihood
PROBABILITY of Failure | Failure Prob | Ranking
Very High: Threat is almost inevitable | >1 in 2 | 10
| 1 in 3 | 9
High: Repeated Threat occurences | 1 in 8 | 8
| 1 in 20 | 7
Moderate: Occasional Threat occurences | 1 in 80 | 6
| 1 in 400 | 5
| 1 in 2,000 | 4
Low: Relatively few Threat occurences | 1 in 15,000 | 3
| 1 in 150,000 | 2
Remote: Threat occurence is unlikely | <1 in 1,500,000 | 1

## Vulnerability
Vulnerability | Ranking
The vulnerability is very exposed and directly, remotely exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 10
The vulnerability is exposed and exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 9
The vulnerability is of very high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 8
The vulnerability is of high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 7
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is partially implemented and somewhat effective. | 6
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is implemented and effective. | 5
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and somewhat effective | 4
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and effective | 3
The vulnerability is not of concern. Relevant security control or other remediation is fully implemented, assessed, and effective | 2
There is no vulenrability | 1